## Roles and Responsibilities
Tasks | Manager | Product Owner | Scrum Master | Development Team
Career development and performance evaluations | R,A | NA | C | I
People Management to handle issues above SM and associate engagement | R,A | NA | C | I
Guide , mentor, provide trainings, coaching, feedback for team | R,A | I/I | R,A | I
Participating in recruitment and hiring new team members | R,A | I/I | I | I
Roadmap discussion | I | R/A | F | I
Take architectural decisions during the architectural reviews | C | I/I | F | R,A
Interaction with BU partners | R,A | I/I | I | I
Provide input on how to make product features better | I | R/A | F,I | I
Do regular meetings with SM and other stake holders to understand any road blocks | R,A | I/NA | C | NA
Work for Organization activities | R,A | I/NA | I | NA
Work with teams on product design , improvement of functionality, facilitate as scrum master | I | I/I | R,A | C
Training and Skill development for the associates | R,A | I/I | C | I
Negotitate and Procure work from BU for expanding existing teams and setting up new teams | R,A | I/NA | I | I
Make the objectives of BU & organization into understandable action ietms | R,A | I/I | I | I
Handling escalations above a Scrum Master | R,A | I/I | C | I
Scrum of scrum meetings participation across locations | R | C/C | F,C | C
Participate in Bi-Weekly Council meetings which review progress of the Roadmap. | R,A | C/C | I,F | I
Review of 'Definition of Done' and make changes | I | C/C | F | R/A
Create a product or project vision | R | A/I | I | I
Document and communicate the vision to team and stakeholders | R | A/C | I | I
Write themes, initiatives, features, epics, and stories to articulate how the vision will be accomplished (the backlog) | C | R/A | C | I,R
Organize the backlog | C | R/R | C,F | I
Prioritize the themes within a release | I | A/R | C,F | I
Prioritize stories within themes | C | R/A | C,F | I
Communicate high level release priorities to stakeholders | R | A/A | C,F | I
Create a release plan | C | R/A | A,F | A
Select what will be worked on in the sprint | C | R/A | F | C
Prioritize the stories in the sprint | C | R/A | F | C
Define acceptance criteria for each story | NA | A/R | I,F | I
Answer questions from developers and testers regarding each story | NA | A/R | F | I
When a story is done review the software either individually or with the developer to determine if the conditions of satisfaction have been met | NA | A/R | F | C
Ensure the flow of business value. | I,C | R/R | R,A | R
Accept the work of the sprint | NA | R/A | C,F | I
Communicate product and release status across the sprints in the release | R | R/A | A,F | I
Manage stakeholder expectations | R | A/R | A, F | I
Meetings: Preperation, Moderation, Post processing | R | I/C | A,F | I,C
Helping teams improve team dynamics | R | I/I | A,F | I,C
Continous improvement of team performace | R,A | I/I | R,A | C
Making Teams self-oragnizing | R | I/I | R,A | C
Help teams remove impediments | R | I,C | R,F | R
Taking the Sprint Goal to 'Done' | A | I/I | F,C | R,A

## Codes
Codes
R | Responsible | Those responsible for the performance(or doing) the task.
A | Accountable | Somebody who should be reached to, in case something not done, and also for the outcome of the task.
C | Consulted | Those whose opinions are sought; and with whom there is two-way communication.
I | Informed | Those who are kept up-to-date on progress; and with whom there is one-way communication.
F | Facilitate | Somebody who should assist the progress of the task in the best possible way.
NA | Not Applicable | This task is not applicable to the concered party